## Agile User Story
AGILE USER STORY
Feature ID | USER STORY ID | PRIORITY | AS A <type of user> | I WANT TO <perform some task> | SO THAT I CAN <achieve some goal> | FINAL STORY
F1 | 1 | High | User | verify and register via email | Iog into the system |  | This section is for the drop-down list
| 2 | High | User | Login into the system | to see the dashboard. |  | High
| 3 | High | User | have a profile | to have all my infromation |  | Medium
F2 | 1 | High | User | have a navigating window | navigate through dashboard |  | Low
| 2 | Medium | User | Edit profile | edit my information when I want to
| 3 | High | User | Upload photos | to have a good profile
F3 | 1 | High | User | Follow user | Follow up to what other users are up to
| 2 | Medium | User | use camera | to take photographs and post it in my profile
| 3 | Medium | User | scroll through my feed | to see other users I have followed.
F4 | 1 | High | User | Access my Gallery | to upload old photographs
| 2 | Medium | User | Like photographs | I can like photos that are good
| 3 | Medium | User | Unlike liked photographs | incase if I like it mistakely.
F5 | 1 | Medium | User | See number of posts | I can have an idea of number of photographs in my account
| 2 | Medium | User | See number of followers and followers | to check the number of followers in my account.
| 3 | Medium | User | See the people I have followed and number of people I have followed. | to check the number of people I have followed.
F6 | 1 | Medium | User | Comment | I can comment on posts I like or dislike.
| 2 | Medium | User | See other comments | I can view comments on posts I have posted
| 3 | High | User | Search users | I can follow the people I like.

## Agile Sprint_1 Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Database Design | 12 |  | Done
Coding | 6 | Sandis Prajapati | Done | 6 | 3 | 2 | 1 | 0 | 0 | 6
Designing | 3 | Bikrum Katwal | Done | 3 | 1 | 1 | 1 | 0 | 0 | 3
Testing | 3 | Sarbajeet G.C | Done | 3 | 0 | 2 | 1 | 0 | 0 | 3
User Registration | 8 |  | Done
Coding | 4 | Bikrum Katwal | Done | 4 | 0 | 0 | 2 | 2 | 0 | 4
Designing | 2 | Sandis Prajapati | Done | 2 | 0 | 0 | 1 | 1 | 0 | 2
Testing | 2 | Sagun Shrestha | Done | 2 | 0 | 0 | 1 | 1 | 0 | 2
User Login | 8 |  | Done
Coding | 4 | Sandis Prajapati | Done | 4 | 0 | 0 | 0 | 2 | 2 | 4
Designing | 2 | Bikrum Katwal | Done | 2 | 0 | 0 | 0 | 1 | 1 | 2
Testing | 2 | Sarbajeet G.C | Done | 2 | 0 | 0 | 0 | 1 | 1 | 2
TOTAL |  |  |  | 28 | 4 | 5 | 7 | 8 | 4 | 28
IDEAL |  |  |  | 22.4 | -1.6 | -0.6 | 1.4 | 2.4 | -1.6 | 22.4
| Remaining Effort | 7
Ideal Trend

## Agile Sprint_2_Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Email Verification | 5 |  | Done
Coding | 3 | Bikrum Katwal | Done | 3 | 2 | 1 | 0 | 0 | 0 | 3
Designing | 1 | Sandis Prajapati | Done | 1 | 1 | 0 | 0 | 0 | 0 | 1
Testing | 1 | Sagun Shrestha | Done | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 1
Task
Home Fragment | 22 |  | Done
Coding | 12 | Sandis Prajapati | Done | 12 | 0 | 5 | 4 | 3 | 0 | 12
Designing | 6 | Bikrum Katwal | Done | 6 | 0 | 3 | 2 | 1 | 0 | 6
Testing | 4 | Sarbajeet G.C | Done | 4 | 0 | 2 | 1 | 1 | 0 | 4
Logout | 2
Coding | 1 | Bikrum Katwal | Done | 1 |  |  |  |  | 1 | 1
Designing | 0 | Sandis Prajapati | Done | 0 |  |  |  |  | 0
Testing | 1 | Sagun Shrestha | Done | 1 |  |  |  |  | 1 | 1
TOTAL |  |  |  | 29 | 3.5 | 11.5 | 7 | 5 | 2 | 29
IDEAL |  |  |  | 23.2 | -2.3 | 5.7 | 1.2 | -0.8 | -3.8 | 23.2
| Remaining Effort | 7
Ideal Trend

## Agile Sprint_3_Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Bottom Navigation View | 6 |  | Done
Coding | 3 | Bikrum Katwal | Done | 3 | 2 | 1 | 0 | 0 | 0 | 3
Designing | 2 | Sandis Prajapati | Done | 2 | 1 | 1 | 0 | 0 | 0 | 2
Testing | 1 | Sarbajeet G.C | Done | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 1
Tab Preparation | 6 |  | Done
Coding | 3 | Bikrum Katwal | Done | 3 | 0 | 2 | 1 | 0 | 0 | 3
Designing | 2 | Sandis Prajapati | Done | 2 | 0 | 1 | 1 | 0 | 0 | 2
Testing | 1 | Sagun Shrestha | Done | 1 | 0 | 0 | 1 | 0 | 0 | 1
Profile toolbar and menu | 15 |  | Done
Coding | 7 | Sandis Prajapati | Done | 7 | 0 | 0 | 3 | 2 | 2 | 7
Designing | 5 | Bikrum Katwal | Done | 5 | 0 | 0 | 2 | 2 | 1 | 5
Testing | 4 | Sarbajeet G.C and Sagun Shrestha | Done | 4 | 0 | 0 | 1 | 1.5 | 1.5 | 4
TOTAL |  |  |  | 28 | 3.5 | 5.5 | 9 | 5.5 | 4.5 | 28 | s
IDEAL |  |  |  | 22.4 | -2.1 | -0.1 | 3.4 | -0.1 | -1.1 | 22.4
| Remaining Effort | 7
Ideal Trend

## Agile Sprint_4_Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Profile | 8 |  | Done
Coding | 5 | Sandis Prajapati | Done | 5 | 3 | 2 | 0 | 0 | 0 | 5
Design | 2 | Bikrum Katwal | Done | 2 | 1 | 1 | 0 | 0 | 0 | 2
Testing | 1 | Sarbajeet G.C | Done | 1 | 0 | 1 | 0 | 0 | 0 | 1
Account Setting | 10 |  | Done
Coding | 5 | Bikrum Katwal | Done | 5 | 0 | 3 | 3 | 0 | 0 | 5
Design | 3 | Sandis Prajapari | Done | 3 | 0 | 2 | 1 | 0 | 0 | 3
Testing | 2 | Sagun Shrestha | Done | 2 | 0 | 1 | 1 | 0 | 0 | 2
Profile Setup | 12 |  | Done
Coding | 7 | Sandis Prajapati and Bikrum Katwal | Done | 7 | 0 | 0 | 3 | 2 | 2 | 8
Design | 3 | Sandis Prajapati and Bikrum Katwal | Done | 3 | 0 | 0 |  | 2 | 1 | 4
Testing | 2 | Sagun Shrestha and Sarbajeet G.C | Done | 2 | 0 | 0 |  | 1 | 1 | 2
TOTAL |  |  |  | 30 | 4 | 10 | 8 | 5 | 4 | 32
IDEAL |  |  |  | 24 | -2 | 4 | 2 | -1 | -2 | 26
| Remaining Effort | 7
Ideal Trend

## Agile Sprint_5_Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Edit Profile | 12 |  | Done
Coding | 6 | Bikrum Katwal | Done | 6 | 2 | 3 | 1 |  |  | 6
Designing | 3 | Sandis Prajapati | Done | 3 | 2 | 1 |  |  |  | 3
Testing | 3 | Sarbajeet G.C, Sagun Shrestha | Done | 3 | 1 | 1 | 1 |  |  | 3
Gallery | 10 |  | Done
Coding | 5 | Sandis Prajapati | Done | 5 |  | 2 | 1 | 1 |  | 5
Designing | 2.5 | Bikrum Katwal | Done | 2.5 |  | 1 | 1.5 |  |  | 2.5
Testing | 2.5 | Sarbajeet G.C, Sagun Shrestha | Done | 2.5 |  | 1.5 | 1 |  |  | 2.5
Camera | 8 |  | Done
Coding | 4 | Bikrum Katwal | Done | 4 |  |  |  | 2 | 2 | 4
Designing | 2 | Sandis Prajapati | Done | 2 |  |  |  | 1 | 1 | 2
Testing | 2 | Sarbajeet G.C, Sagun Shrestha | Done | 2 |  |  |  | 1 | 1 | 2
TOTAL |  |  |  | 30 | 5 | 9.5 | 5.5 | 5 | 4 | 30
IDEAL |  |  |  | 24 | -1 | 3.5 | -0.5 | -1 | -2 | 24
| Remaining Effort | 7
Ideal Trend

## Agile Sprint_6_Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Image view | 12 |  | Done
Coding | 6 | Bikrum Katwal | Done | 6 | 2 | 3 | 1 |  |  | 6
Designing | 3 | Sandis Prajapati | Done | 3 | 2 | 1 |  |  |  | 3
Testing | 3 | Sarbajeet G.C, Sagun Shrestha | Done | 3 | 1 | 1 | 1 |  |  | 3
Firebase Storage | 10 |  | Done
Coding | 5 | Sandis Prajapati | Done | 5 |  | 2 | 1 | 1 |  | 5
Designing | 2.5 | Bikrum Katwal | Done | 2.5 |  | 1 | 1.5 |  |  | 2.5
Testing | 2.5 | Sarbajeet G.C, Sagun Shrestha | Done | 2.5 |  | 1.5 | 1 |  |  | 2.5
Comment | 8 |  | Done
Coding | 4 | Bikrum Katwal | Done | 4 |  |  |  | 2 | 2 | 4
Designing | 2 | Sandis Prajapati | Done | 2 |  |  |  | 1 | 1 | 2
Testing | 2 | Sarbajeet G.C, Sagun Shrestha | Done | 2 |  |  |  | 1 | 1 | 2
TOTAL |  |  |  | 30 | 5 | 9.5 | 5.5 | 5 | 4 | 30
IDEAL |  |  |  | 24 | -1 | 3.5 | -0.5 | -1 | -2 | 24
| Remaining Effort | 7
Ideal Trend

## Agile Sprint_7_Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Main News Feed | 12 |  | Done
Coding | 6 | Bikrum Katwal | Done | 6 | 2 | 3 | 1 |  |  | 6
Designing | 3 | Sandis Prajapati | Done | 3 | 2 | 1 |  |  |  | 3
Testing | 3 | Sarbajeet G.C, Sagun Shrestha | Done | 3 | 1 | 1 | 1 |  |  | 3
Like | 10 |  | Done
Coding | 5 | Sandis Prajapati | Done | 5 |  | 2 | 1 | 1 |  | 5
Designing | 2.5 | Bikrum Katwal | Done | 2.5 |  | 1 | 1.5 |  |  | 2.5
Testing | 2.5 | Sarbajeet G.C, Sagun Shrestha | Done | 2.5 |  | 1.5 | 1 |  |  | 2.5
Debugging | 8 |  | Done
Coding | 4 | Bikrum Katwal | Done | 4 |  |  |  | 2 | 2 | 4
Designing | 2 | Sandis Prajapati | Done | 2 |  |  |  | 1 | 1 | 2
Testing | 2 | Sarbajeet G.C, Sagun Shrestha | Done | 2 |  |  |  | 1 | 1 | 2
TOTAL |  |  |  | 30 | 5 | 9.5 | 5.5 | 5 | 4 | 30
IDEAL |  |  |  | 24 | -1 | 3.5 | -0.5 | -1 | -2 | 24
| Remaining Effort | 7
Ideal Trend